## Sheet1
Project Plan
Actual weeknumber |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Project weeknumber |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Task | Project planning and research | bar: 6 1 to 9 4
Implementing Raspberry Pi as a hub | bar: 10 5 to 14 9
ZigBee testing and implementation (creating smart devices) | bar: 11 6 to 14 9
Easter holiday | bar: 15 10
Creating Android app | bar: 13 8 to 14 9; 16 11 to 19 14
Exam period | bar: 20 15 to 21 16
Creating smart devices | bar: 22 17 to 24 19
Merging smart devices, app, and hub into a final product | bar: 24 19 to 25 20
Writing report | bar: 25 20 to 27 22